## Sheet1
Task | Week | Labiba (hrs) | Munib (hrs) | Notes
Group formation | 1 | 1 | 1 | Done in Week 1
Project proposal | 2 | 4 | 1 | Labiba lead content
Project plan | 2 | 3 | 2 | Shared
Baseline demo | 3 | 1 | 6 | Munib leads ROS2
Metrics setup | 3 | 2 | 3 | Logging + evaluation
PPO integration | 4 | 6 | 3 | Labiba leads PPO node
Reward shaping | 4–5 | 5 | 0 | 100% RL work
Training & tuning | 5 | 6 | 2 | Mainly RL
Evaluation | 6 | 3 | 4 | Shared testing
Final report | 7 | 4 | 2 | Labiba lead RL sections
Final presentation | 7 | 3 | 2 | Both present
total hours |  | 38 | 26